## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Setup of the environment |  | 45 | 45 | 0 |  |  |  | 11 | 100%
1.1 | Database + containerization of DB | Carlo | 10 | 10 | 0 | 1 | 2023-01-17 | 2023-01-18 | 2 | 100% | bar: WEEK 1 T to WEEK 1 W
1.2 | Setup of all the containers | Daniel | 10 | 10 | 0 | 1 | 2023-01-17 | 2023-01-18 | 2 | 100% | bar: WEEK 1 T to WEEK 1 W
1.3 | Connecting all the microservices | Daniel | 15 | 15 | 0 | 1 | 2023-01-19 | 2023-01-23 | 5 | 100% | bar: WEEK 1 R to WEEK 2 F
1.4 | Warehouse Management Microservice | Daniel | 10 | 10 | 0 | 1 | 2023-01-24 | 2023-01-25 | 2 | 100%
2 | Backend development |  | 40 | 40 | 0 |  |  |  | 10 | 100%
2.1 | Product Catalog Microservice | Christian | 15 | 15 | 0 | 2 | 2023-01-19 | 2023-01-23 | 5 | 100% | bar: WEEK 1 R to WEEK 2 F
2.2 | Login setup | Carlo | 10 | 10 | 0 | 2 | 2023-01-24 | 2023-01-25 | 2 | 100%
2.3 | Purchase Refund Microservice | Christian | 10 | 10 | 0 | 2 | 2023-01-26 | 2023-01-27 | 2 | 100%
2.4 | Testing the backend | Daniel | 5 | 5 | 0 | 2 | 2023-01-31 | 2023-01-31 | 1 | 100% | bar: WEEK 3 T
3 | Frontend development |  | 80 | 80 | 0 |  |  |  | 30 | 100%
3.1 | React Setup | Carlo | 15 | 15 | 0 | 3 | 2023-02-01 | 2023-02-03 | 3 | 100% | bar: WEEK 3 W to WEEK 3 F
3.2 | Homepage + Merchant Panel | Christian | 15 | 15 | 0 | 3 | 2023-02-06 | 2023-02-08 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W
3.3 | Add product Modal | Christian | 10 | 10 | 0 | 3 | 2023-02-09 | 2023-02-10 | 2 | 100% | bar: WEEK 4 R to WEEK 5 F
3.4 | Search + Details + Sort Products | Christian | 15 | 15 | 0 | 3 | 2023-02-13 | 2023-02-15 | 3 | 100%
3.5 | Login and Registration | Daniel | 10 | 10 | 0 | 3 | 2023-02-16 | 2023-02-17 | 2 | 100%
3.6 | Customer Functionalities Finished | Christian | 15 | 15 | 0 | 3 | 2023-02-20 | 2023-02-26 | 7 | 100% | bar: WEEK 5 M to WEEK 6 F
4 | Finalization of functionalities and testing |  | 58 | 58 | 0 |  |  |  | 15 | 100%
4.1 | Completion of Database | Carlo | 10 | 10 | 0 | 4 | 2023-03-01 | 2023-03-04 | 4 | 100%
4.2 | Checkout + Cart Update | Daniel | 10 | 10 | 0 | 4 | 2023-03-06 | 2023-03-09 | 4 | 100% | bar: WEEK 8 M to WEEK 9 R
4.3 | Admin / Customer Login | Daniel | 5 | 5 | 0 | 4 | 2023-03-10 | 2023-03-10 | 1 | 100% | bar: WEEK 9 F
4.4 | All Admin Functionalities added(Add/Remove) | Christian | 10 | 10 | 0 | 4 | 2023-03-13 | 2023-03-15 | 3 | 100% | bar: WEEK 10 M to WEEK 10 W
4.5 | Quick fix on Customer Functionalities(Search, ordering) | Daniel | 3 | 3 | 0 | 4 | 2023-03-16 | 2023-03-16 | 1 | 100% | bar: WEEK 10 R
4.6 | Logout | Daniel | 5 | 5 | 0 | 4 | 2023-03-20 | 2023-03-21 | 2 | 100%
4.7 | Testing of the whole system | Carlo | 15 | 15 | 0 | 4 | 2023-03-22 | 2023-03-25 | 4 | 100%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS worked in total (if we worked the same day we count it as 1 day) | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 223 | 223 | 0 | 66 | 3.3788 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 223 | 223 | 223 | 223 | 219.6212 | 216.2424 | 212.8636 | 209.4848 | 206.1061 | 202.7273 | 199.3485 | 195.9697 | 192.5909 | 189.2121 | 185.8333 | 182.4545 | 179.0758 | 175.697 | 172.3182 | 168.9394 | 165.5606 | 162.1818 | 158.803 | 155.4242 | 152.0455 | 148.6667 | 145.2879 | 141.9091 | 138.5303 | 135.1515 | 131.7727 | 128.3939 | 125.0152 | 121.6364 | 118.2576 | 114.8788 | 111.5 | 108.1212 | 104.7424 | 101.3636 | 97.9848 | 94.6061 | 91.2273 | 87.8485 | 84.4697 | 81.0909 | 77.7121 | 74.3333 | 70.9545 | 67.5758 | 64.197 | 60.8182 | 57.4394 | 54.0606 | 50.6818 | 47.303 | 43.9242 | 40.5455 | 37.1667 | 33.7879 | 30.4091 | 27.0303 | 23.6515 | 20.2727 | 16.8939 | 13.5152 | 10.1364 | 6.7576 | 3.3788 | 1.9185e-13
[10 empty] | ESTIMATE | 223 | 223 | 223 | 223 | 218 | 213 | 210 | 207 | 204 | 198 | 195 | 191 | 185 | 178 | 173 | 168 | 163 | 158 | 153 | 150 | 147 | 144 | 140 | 137 | 133 | 129 | 126 | 123 | 120 | 117 | 114 | 110 | 106 | 102 | 98 | 90 | 83 | 79 | 75 | 71 | 68 | 66 | 63 | 60 | 58 | 56 | 53 | 50 | 48 | 46 | 41 | 37 | 34 | 29 | 26 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 |  |  | 6439
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 0 | 0 | 0 | 5 | 5 | 3 | 3 | 3 | 6 | 3 | 4 | 6 | 7 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 8 | 7 | 4 | 4 | 4 | 3 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 2 | 5 | 4 | 3 | 5 | 3 | 5 | [15 empty] | 202
[10 empty] | HRS REMAINING | 223 | 223 | 223 | 218 | 213 | 210 | 207 | 204 | 198 | 195 | 191 | 185 | 178 | 173 | 168 | 163 | 158 | 153 | 150 | 147 | 144 | 140 | 137 | 133 | 129 | 126 | 123 | 120 | 117 | 114 | 110 | 106 | 102 | 98 | 90 | 83 | 79 | 75 | 71 | 68 | 66 | 63 | 60 | 58 | 56 | 53 | 50 | 48 | 46 | 41 | 37 | 34 | 29 | 26 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 0 | 0 | 6237
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Create a new canva, draw by hand, choose the thickness of the draw and the colors | Basics to draw | In this sprint, the main goal is to deliver a basic drawing software to get our starting point (just the ability to draw simple things) | Alexandre | 24 | Completed | This is the starting point for our software, we need it clean before starting to add other features. | Not Started | 1
High | 2 | Register, open existing drawing, close the current drawing, quit the application | File gestion | One important thing is to be able to get back to a previous work so we need to add a register and open options. Closing the canva will help the user to create a new drawing without stop and launch again the code | Marcin | 24 | Completed | Now that we can draw simply, it's mandatory that the users can register his drawing and open it again if he wants to change it. | In Progress | 2
Medium | 3 | Adding new figures to draw, ability to fill those and select them | New Figures | We want to offet the user more options to improve his drawing, by adding figures and be able to select them (this options will be used for the next sprints) | Alexandre | 80 | Completed | From now it just comes to add features that will improve the user experience, the select option will be reused in the next sprint. | Completed | 4
Medium | 4 | Delete, Undo, move the figures, put in front, back, forefront and background | Modify the drawing | The user will be able to modify his current drawing, by modifying its position (put in the foreground of the drawing, on the background, on step behind or one step ahead) | Marcin | 40 | Completed | By first selecting the wanted parts, the user will be able to move and change his drawing with new features. |  | 8
High | 5 | Dockerization of the project and realising the documentation | Finalization of the project | This is the final step for the project, we made the documentation (specification and conception) and managed to put the project on docker so that anyone can launch it even without the best configuration | Alexandre & Marcin | 40 | Completed | After finishing the project, the goal is to be able to launch the project without the needed configuration, to do this we will add the docker files and compilation. The documentation will explain everything about the project. |  | 16
24
40
80