## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Setup of the environment |  | 45 | 45 | 0 |  |  |  | 11 | 100%
1.1 | Database + containerization of DB | Carlo | 10 | 10 | 0 | 1 | 44943 | 44944 | 2 | 100% | bar: WEEK 1 T to WEEK 1 W
1.2 | Setup of all the containers | Daniel | 10 | 10 | 0 | 1 | 44943 | 44944 | 2 | 100% | bar: WEEK 1 T to WEEK 1 W
1.3 | Connecting all the microservices | Daniel | 15 | 15 | 0 | 1 | 44945 | 44949 | 5 | 100% | bar: WEEK 1 R to WEEK 2 F
1.4 | Warehouse Management Microservice | Daniel | 10 | 10 | 0 | 1 | 44950 | 44951 | 2 | 100%
2 | Backend development |  | 40 | 40 | 0 |  |  |  | 10 | 100%
2.1 | Product Catalog Microservice | Christian | 15 | 15 | 0 | 2 | 44945 | 44949 | 5 | 100% | bar: WEEK 1 R to WEEK 2 F
2.2 | Login setup | Carlo | 10 | 10 | 0 | 2 | 44950 | 44951 | 2 | 100%
2.3 | Purchase Refund Microservice | Christian | 10 | 10 | 0 | 2 | 44952 | 44953 | 2 | 100%
2.4 | Testing the backend | Daniel | 5 | 5 | 0 | 2 | 44957 | 44957 | 1 | 100% | bar: WEEK 3 T
3 | Frontend development |  | 80 | 80 | 0 |  |  |  | 30 | 100%
3.1 | React Setup | Carlo | 15 | 15 | 0 | 3 | 44958 | 44960 | 3 | 100% | bar: WEEK 3 W to WEEK 3 F
3.2 | Homepage + Merchant Panel | Christian | 15 | 15 | 0 | 3 | 44963 | 44965 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W
3.3 | Add product Modal | Christian | 10 | 10 | 0 | 3 | 44966 | 44967 | 2 | 100% | bar: WEEK 4 R to WEEK 5 F
3.4 | Search + Details + Sort Products | Christian | 15 | 15 | 0 | 3 | 44970 | 44972 | 3 | 100%
3.5 | Login and Registration | Daniel | 10 | 10 | 0 | 3 | 44973 | 44974 | 2 | 100%
3.6 | Customer Functionalities Finished | Christian | 15 | 15 | 0 | 3 | 44977 | 44983 | 7 | 100% | bar: WEEK 5 M to WEEK 6 F
4 | Finalization of functionalities and testing |  | 58 | 58 | 0 |  |  |  | 15 | 100%
4.1 | Completion of Database | Carlo | 10 | 10 | 0 | 4 | 44986 | 44989 | 4 | 100%
4.2 | Checkout + Cart Update | Daniel | 10 | 10 | 0 | 4 | 44991 | 44994 | 4 | 100% | bar: WEEK 8 M to WEEK 9 R
4.3 | Admin / Customer Login | Daniel | 5 | 5 | 0 | 4 | 44995 | 44995 | 1 | 100% | bar: WEEK 9 F
4.4 | All Admin Functionalities added(Add/Remove) | Christian | 10 | 10 | 0 | 4 | 44998 | 45000 | 3 | 100% | bar: WEEK 10 M to WEEK 10 W
4.5 | Quick fix on Customer Functionalities(Search, ordering) | Daniel | 3 | 3 | 0 | 4 | 45001 | 45001 | 1 | 100% | bar: WEEK 10 R
4.6 | Logout | Daniel | 5 | 5 | 0 | 4 | 45005 | 45006 | 2 | 100%
4.7 | Testing of the whole system | Carlo | 15 | 15 | 0 | 4 | 45007 | 45010 | 4 | 100%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS worked in total (if we worked the same day we count it as 1 day) | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 223 | 223 | 0 | 66 | 3.3788 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 223 | 223 | 223 | 223 | 219.6212 | 216.2424 | 212.8636 | 209.4848 | 206.1061 | 202.7273 | 199.3485 | 195.9697 | 192.5909 | 189.2121 | 185.8333 | 182.4545 | 179.0758 | 175.697 | 172.3182 | 168.9394 | 165.5606 | 162.1818 | 158.803 | 155.4242 | 152.0455 | 148.6667 | 145.2879 | 141.9091 | 138.5303 | 135.1515 | 131.7727 | 128.3939 | 125.0152 | 121.6364 | 118.2576 | 114.8788 | 111.5 | 108.1212 | 104.7424 | 101.3636 | 97.9848 | 94.6061 | 91.2273 | 87.8485 | 84.4697 | 81.0909 | 77.7121 | 74.3333 | 70.9545 | 67.5758 | 64.197 | 60.8182 | 57.4394 | 54.0606 | 50.6818 | 47.303 | 43.9242 | 40.5455 | 37.1667 | 33.7879 | 30.4091 | 27.0303 | 23.6515 | 20.2727 | 16.8939 | 13.5152 | 10.1364 | 6.7576 | 3.3788 | 0
[10 empty] | ESTIMATE | 223 | 223 | 223 | 223 | 218 | 213 | 210 | 207 | 204 | 198 | 195 | 191 | 185 | 178 | 173 | 168 | 163 | 158 | 153 | 150 | 147 | 144 | 140 | 137 | 133 | 129 | 126 | 123 | 120 | 117 | 114 | 110 | 106 | 102 | 98 | 90 | 83 | 79 | 75 | 71 | 68 | 66 | 63 | 60 | 58 | 56 | 53 | 50 | 48 | 46 | 41 | 37 | 34 | 29 | 26 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 |  |  | 6439
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 0 | 0 | 0 | 5 | 5 | 3 | 3 | 3 | 6 | 3 | 4 | 6 | 7 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 8 | 7 | 4 | 4 | 4 | 3 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 2 | 5 | 4 | 3 | 5 | 3 | 5 | [15 empty] | 202
[10 empty] | HRS REMAINING | 223 | 223 | 223 | 218 | 213 | 210 | 207 | 204 | 198 | 195 | 191 | 185 | 178 | 173 | 168 | 163 | 158 | 153 | 150 | 147 | 144 | 140 | 137 | 133 | 129 | 126 | 123 | 120 | 117 | 114 | 110 | 106 | 102 | 98 | 90 | 83 | 79 | 75 | 71 | 68 | 66 | 63 | 60 | 58 | 56 | 53 | 50 | 48 | 46 | 41 | 37 | 34 | 29 | 26 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 0 | 0 | 6237
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Having the whole environment ready | Setup of the Environment | In this sprint our objective was to have the db and the microservices all connected and containerized |  | 40 | Completed |  | Not Started | 1
High | 2 | Implementing the backend functionalities | Backend Development | We worked strictly on the Backend of the microservices, by working and testing all the endpoints(Postman) |  | 40 | Completed |  | In Progress | 2
High | 3 | Implementing the frontend functionalities | Frontend Development | We worked on React for the connection between Backend and Frontend and the development of the first functionalities |  | 80 | Completed |  | Completed | 4
Medium | 4 | Finalization of the system | Finalization and testing | Implementation of the last functionalities, testing of them and of the whole system fully deployed |  | 40 | Completed |  |  | 8
16
24
40
80